## Task_Table
ID | Name | Duration | Predecessors | Outline Level | Project Notes
0 | New Product Launch | 15 days |  | 0
1 | New Site Launch Preparation | 15 days |  | 1
2 | Phase 1 - Planning | 8 days |  | 2
3 | Identify the launch team | 2 days |  | 3 | The launch team will be the same as last time
4 | Determine site objectives | 1 day | 3 | 3
5 | Identify budget requirements | 1 day | 4 | 3
6 | Obtain launch budget approval | 1 day | 5 | 3
7 | Define launch goals (launch timing and publicity objectives) | 1 day | 6 | 3
8 | Send RFQ | 1 day | 7 | 3
9 | Identify technology partners | 1 day | 8 | 3
10 | Planning COMPLETE | 0 days | 9 | 3
11 | Phase 2 - Development | 6 days |  | 2
12 | Define creative brief | 3 days | 10 | 3
13 | Set design scope | 1 day | 12 | 3 | Scope will need review sessions
14 | Create design | 1 day | 13 | 3
15 | Create code | 1 day | 14 | 3
16 | Development Phase COMPLETE | 0 days | 15 | 3
17 | Phase 3 - Execution | 1 day |  | 2
18 | Upload fles and data | 1 day | 16 | 3
19 | Launch Site | 0 days | 18 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Steve Masters | E | Work |  | PMO |  |  | 100% | $0.00/h | 0
2 | Rob Young | M | Work |  | DEV |  |  | 100% | $0.00/h | 0
3 | Kim Ralls | M | Work |  | PMO |  |  | 100% | $0.00/h | 0
4 | Suzy Queue | S | Work |  | DEV |  |  | 100% | $0.00/h | 0
5 | Aaron Painter | P | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Project Manager | F | Work |  |  |  |  | 100% | $0.00/h | 0
7 | BA | P | Work |  |  |  |  | 100% | $0.00/h | 0